26  06

FLLS 2027 – 2031 Plan of Service Timeline

Plan of Service

- January 2026

  - FLLS staff meeting to review previous Plan of Service and current questions

  - Review and formulate focus group questions

  - Begin conversations and outline our timeframe to the FLLS Directors

- February 2026

  - FLLS staff focus group

- March 2026

  - Begin county-wide in-person focus groups

  - FLLS Board of Trustees focus group

- April 2026

  - Finalize county-wide in-person focus groups

  - Virtual focus groups for library staff/trustees who can’t attend in person

- May 2026

  - In-depth electronic survey for members

  - Begin developing draft Plan

- June - July 2026

  - Develop draft Plan

- August 2026

  - Finalize Plan of Service

- September 2026

  - FLLS Board Vote on Plan

- October 2026

  - Submit on October 1, 2026

Continued…

FLLS  2027 – 2031 Plan of Service Timeline   p. 2

Free Direct Access Plan

- January 2026:  Create Free Direct Access Plan Subcommittee during Plan of Service Committee meeting. To be made up of Plan of Service Committee members and member library representatives.

- February 2026: Meet to discuss the current Free Direct Access Plan, the process and how it relates to the Plan of Service. Start discussions at FALCONS.

- March – April 2026:  Revisions of Free Direct Access Plan

- May 2026: Discussion at FALCONS

- June 2026: Document ready to go out to member library boards

- June – August 2026:  Member library board votes

- September 2026: FLLS Board Vote

- October 2026: Submission on October 1 along with Plan of Service

Central Library Plan of Service

- January 2026: Create Free Direct Access Plan Subcommittee during Plan of Service Committee meeting.  To be made up of Plan of Service Committee Members and member library representatives.

- February 2026: Meet to discuss the current Central Library Plan of Service, the process and how it relates to the Plan of Service.

- March – April: Include Central Library questions in focus groups

- April – June: Start creating Central Library Plan of Service

- July – August: Central Library Plan of Service vote at Central Library

- August – September: Central Library Plan of Service vote at FLLS

- October 2026: Submission on October 1 along with Plan of Service